## 12th Grade
Steps will be highlighted if A and R are not assigned.
[5 empty] | R: | Does the step
Grade-Level RACI Chart |  |  |  |  | A: | Accountable for the step
[5 empty] | C: | Consulted with before the step
[5 empty] | I: | Informed when the step is completed
| Category: | Project Administration
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| GEAR UP team (at least one district administrator, at least one building administrator, school counselor(s), all GEAR UP paid staff, and other school staff such as class advisors) shall meet at least monthly to ensure that the work plan is followed. | N/A | [6 empty] | Workplan | N/A
| Submit match documentation including a summary of all match collected and the backup documentation from each contributor or source. This requirement is waived for 2022-2023. | N/A | The 25th of each month | [5 empty] | http://gearup.wa.gov/grant-management | In-Kind Match Form (Goods & Services) In-Kind Match Form (School & Staff) Monthly Match Summary Form
| Submit GEAR UP expenditures for reimbursement. | N/A | The 25th of each month | [5 empty] | http://gearup.wa.gov/grant-management | A19, Travel Expense Voucher
| Participate in annual site visits with WSAC-Washington State GEAR UP staff and/or the external evaluators to ensure program compliance and effectiveness. | N/A | As scheduled. | R | R |  | R
| Track student, family, and staff participation in GEAR UP sponsored activities using program sign-in sheets. Activity and participation data will be entered electronically at least weekly into the WSAC-Washington State GEAR UP portal/database. | N/A | Weekly | R |  |  |  |  | http://gearup.wa.gov/grant-management
| Submit an annual work plan and budget. | N/A | 2023-06-30 | R | R |  | R |  | Templates and instructions will be provided.
| When requested, administer and collect student, parent, and educator surveys and meet minimum return rates. | N/A | Annually, spring | R |  |  |  |  | Surveys will be provided.
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Professional Development
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Attend GEAR UP West Conference. | GEAR UP Sponsored Professional Development | October, annually | [5 empty] | http://gearup.wa.gov/about/what-we-do/gear-west | Portal
| Attend WAGU Winter Workshop | GEAR UP Sponsored Professional Development | See calendar | [5 empty] | http://gearup.wa.gov/calendar | Portal
| Attend WAGU Spring Workshop | GEAR UP Sponsored Professional Development | See calendar | [5 empty] | http://gearup.wa.gov/calendar | Portal
| Attend Summer WAGU Kick-Off and Training Workshop. | GEAR UP Sponsored Professional Development | August | [5 empty] | http://gearup.wa.gov/calendar | Portal
| Watch WAGU webinars. | GEAR UP Sponsored Professional Development | TBD | [5 empty] | https://www.youtube.com/channel/UC8v9AT7pG9bWwf9XcBYQptA | Portal
| Category: | Staff Activities
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Make GEAR UP sponsored professional development available to all appropriate staff at both the middle and high school levels. | GEAR UP Sponsored Professional Development | [6 empty] | Workshops, NCCEP Study Lab Couses, NCAN E-learning | Portal
| Provide a program orientation and match training to all building staff to ensure that they understand the program and the opportunities available to them. The match training must include what is allowable as match and how to document match accurately using GEAR UP forms. | Pro-Dev Staff Orientation and Match Training | No later than October 31 | [5 empty] | Washington State GEAR UP training templates | Portal
| Educator Survey - 90% of building staff will complete an educator survey in Spring 2023. | Other | May | R |  |  | I/C |  | WSAC will provide an electronic survey in Spring. | Portal
| Category: | Advisory Committee
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Establish an advisory committee and convene once per year to provide guidance and build community acceptance and support of GEAR UP, and create a college-going culture within the school and community. |  | Provide a roster of Advisory Committee members to WSAC via the portal by November 1 of each year. | [6 empty] | Agendas and meeting minutes from these meetings must be kept on file and available for site visits. Submit roster, meeting agendas and minutes to WSAC via the portal.
| GEAR UP Advisory Committee Meeting #1 |  | November
| GEAR UP Advisory Committee Meeting #2 |  | May
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Student Activities
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| National GEAR UP Week: You are required to hold at least one event during this week. You are encouraged to conduct your student and family orientations during this time, or provide another “kick-off” event to celebrate GEAR UP. | Other | September 26-30, 2022 | [5 empty] | http://gearup.wa.gov/about/impact/national-gear-week | Portal
| Provide GEAR UP Student Orientation. | Student Orientation | No later than October 31 | [5 empty] | WAGU Templates | Portal
| Help students update washboard profile & CBS contact information. | Financial Aid Counseling/Advising | [7 empty] | Portal
| Assist students in successfully updating their High School and Beyond Plan. | Counseling/Advising/Academic Planning/Career Counseling | [6 empty] | https://www.k12.wa.us/student-success/graduation/graduation-requirements/high-school-beyond-plan/career-guidance-washington-lesson-plans | Portal
| Assist students in successfully completing senior year math to ensure college-level ready. | Tutoring and Homework Assistance | [7 empty] | Portal
| Provide a financial literacy curriculum that meets the state standards. | Financial Aid Counseling/Advising | [7 empty] | Portal
| Assist students in developing and revising their high school course plan to ensure they will meet the minimum college admissions standards. Encourage students to take dual credit and other challenging courses. | Counseling/Advising/Academic Planning/Career Counseling | September-May | [5 empty] | https://www.k12.wa.us/student-success/graduation/graduation-requirements/high-school-beyond-plan/career-guidance-washington-lesson-plans | Portal
| Provide tutoring and homework help to help students earn a minimum cumulative GPA of 3.0 on a 4.0 scale. | Tutoring and Homework Assistance | [7 empty] | Portal
| Provide test preparation activities: Accuplacer or community college assessment. Share results with families and advisors for course enrollment planning. | Tests/Test Preparation | [6 empty] | https://accuplacer.collegeboard.org/student/practice | Portal
| Administer the Accuplacer. |  | Mar.-Jun.
| Assist in student-led conferences. | Family Events-Counseling and Advising | [6 empty] | https://www.k12.wa.us/student-success/graduation/graduation-requirements/high-school-beyond-plan/career-guidance-washington-lesson-plans | Portal
| Assist in advisory program such as Career Guidance Washington. | Counseling/Advising/Academic Planning/Career Counseling | September-May | [5 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade11.aspx | Portal
| Meet w/ students who are off track on meeting grad requirements. | Counseling/Advising/Academic Planning/Career Counseling | March | [5 empty] | MTSS/Check and Connect | Portal
| Establish mentoring program such as Check and Connect or similar targeting students at risk of failing classes, falling behind academically, or with attendance issues. | Comprehensive Mentoring | [6 empty] | Check and Connect/Mentoring Works | Portal
| Host the 12th Year Campaign. |  | Oct.-Nov. | [5 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Assist students in completing 3 or more postsecondary applications. | [7 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Assist students and families in completing the WASFA and FAFSA. |  | Oct.-Nov. | [5 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Assist students and Families with Student Aid Reports (SAR). |  | Feb. | [5 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Help w/ financial aid award comparison. |  | April | [5 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Scholarship promotion and assistance |  | Sept. -Jun.
| Host Decision Day or College Signing Day |  | May | [5 empty] | http://www.readysetgrad.org/signing-day
| Summer Camp/Bridge | Summer Programs - Academic Enrichment, Summer Programs-Fee Only, or Summer Programs-Remedial | July-Aug.
| Texting Campaign. |  | July-Aug.
| Transition Activities. |  | Apr-Jun.
| Category: | Family Activities
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Provide a minimum of three (3) workshops per year to help families understand how to prepare for careers and college, including high school graduation requirements, college entrance requirements, financial aid, scholarships, and financial literacy. | Family Events | [6 empty] | Family Engagement Resource Guide | Portal
| Provide a Family Event: Family Orientation | Family Event - Orientation or Celebratory | No later than October 31 | [5 empty] | WAGU Templates | Portal
| Family Event #1: College admissions procedures and FAFSA/WASFA completion & scholarships | Family Events | Fall | [5 empty] | WAGU Templates | Portal
| Family Event #2: Fit/Match, Commitment, Senior Signing Day | Family Events | Winter | [5 empty] | WAGU Templates | Portal
| Family Event #3: Transition to college | Family Events | Spring | [5 empty] | WAGU Templates | Portal
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities