## 7-12
Steps will be highlighted if A and R are not assigned.
[5 empty] | R: | Does the step
Grade-Level RACI Chart |  |  |  |  | A: | Accountable for the step
[5 empty] | C: | Consulted with before the step
[5 empty] | I: | Informed when the step is completed
| Category: | Project Administration
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| GEAR UP team (at least one district administrator, at least one building administrator, school counselor(s), all GEAR UP paid staff, and other school staff such as class advisors) shall meet at least monthly to ensure that the work plan is followed. | N/A | [6 empty] | Workplan
| Submit match documentation including a summary of all match collected and the backup documentation from each contributor or source. | N/A | The 25th of each month | [5 empty] | http://gearup.wa.gov/grant-management | In-Kind Match Form (Goods & Services) In-Kind Match Form (School & Staff) Monthly Match Summary Form
| Submit GEAR UP expenditures for reimbursement. | N/A | The 25th of each month | [5 empty] | http://gearup.wa.gov/grant-management | A19, Travel Expense Voucher
| Participate in annual site visits with WSAC-Washington State GEAR UP staff and/or the external evaluators to ensure program compliance and effectiveness. | N/A | As scheduled. | R |  |  | R
| Track student, family, and staff participation in GEAR UP sponsored activities using program sign-in sheets. Activity and participation data will be entered electronically at least weekly into the WSAC-Washington State GEAR UP portal/database. | N/A | Weekly | R |  |  |  |  | http://gearup.wa.gov/grant-management | Portal
| Submit an annual work plan and budget. | N/A | 2019-06-30 | [5 empty] | Templates and instructions will be provided.
| When requested, administer and collect student and parent surveys and meet minimum return rates. | N/A | Annually, spring | R |  |  |  |  | Surveys will be provided.
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Professional Development
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Attend Annual GEAR UP West Conference. | GEAR UP Sponsored Professional Development | Oct. 14-16, 2018 | [5 empty] | http://gearup.wa.gov/about/what-we-do/gear-west | Portal
| Attend WAGU March Workshop | GEAR UP Sponsored Professional Development | March | [5 empty] | http://gearup.wa.gov/calendar | Portal
| Attend WAGU April Workshop | GEAR UP Sponsored Professional Development | April | [5 empty] | http://gearup.wa.gov/calendar | Portal
| Attend Summer WAGU Kick-Off and Training Workshop. | GEAR UP Sponsored Professional Development | August | [5 empty] | http://gearup.wa.gov/calendar | Portal
| Conduct Staff Orientation and Match Training. | GEAR UP Sponsored Professional Development | By October 31
| Watch WAGU webinars. | GEAR UP Sponsored Professional Development | Nov, Dec, Jan, Feb, Apr, May | [5 empty] | https://www.youtube.com/channel/UC8v9AT7pG9bWwf9XcBYQptA | Portal
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Staff Activities
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Make GEAR UP sponsored professional development available to all appropriate staff at both the middle and high school levels. | GEAR UP Sponsored Professional Development | [6 empty] | Workshops, GoAlliance Courses, NCAN Elearning | Portal
| Provide a program orientation and match training to all building staff to ensure that they understand the program and the opportunities available to them. The match training must include what is allowable as match and how to document match accurately using GEAR UP forms. | Pro-Dev Staff Orientation and Match Training | No later than October 31 | [5 empty] | Washington State GEAR UP training templates | Portal
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Advisory Committee
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Establish an advisory committee and convene twice per year to provide guidance and build community acceptance and support of GEAR UP, and create a college-going culture within the school and community. |  | Provide a roster of Advisory Committee members to WSAC via the portal by November 1 of each year. | [6 empty] | Agendas and meeting minutes from these meetings must be kept on file and available for site visits. Submit roster, meeting agendas and minutes to WSAC via the portal.
GEAR UP Advisory Committee Meeting #1
GEAR UP Advisory Committee Meeting #2
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Student Activities
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
What Works Clearinghouse Recommendation 1: Offer courses and curricula that prepare students for postsecondary level work and ensure that students understand what constitutes a postsecondary-ready curriculum by 9th grade.
| Assist 8th-12th grade students in successfully beginning and updating their High School and Beyond Plan. | Counseling/Advising/Academic Planning/Career Counseling | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade8.aspx | Portal
| Provide tutoring and homework help to help 7th-12th grade students earn a minimum cumulative GPA of 3.0 on a 4.0 scale. | Tutoring and Homework Assistance | [7 empty] | Portal
| Assist 7th and 8th grade students in preparing for pre-algebra. | Tutoring and Homework Assistance | [7 empty] | Portal
| Assist 9th grade students in successfully completing Algebra I. | Tutoring and Homework Assistance | [7 empty] | Portal
| Assist 10th grade students in successfully completing Geometry. | Tutoring and Homework Assistance | [7 empty] | Portal
| Assist 11th grade students in successfully completing Algebra II. | Tutoring and Homework Assistance | [7 empty] | Portal
| Assist students in successfully completing senior year math to ensure college-level ready. | Tutoring and Homework Assistance | [7 empty] | Portal
| Host transition activities for 8th grade students. | Counseling/Advising/Academic Planning/Career Counseling | Apr-Jun. | [6 empty] | Portal
| Host transition activities for 12th grade students. | Counseling/Advising/Academic Planning/Career Counseling | Apr-Jun. | [6 empty] | Portal
| Support academic/remedial summer experiences to ensure 7th-12th grade students stay on track to graduate. | Summer Programs - Academic Enrichment, Summer Programs-Fee Only, or Summer Programs-Remedial | [7 empty] | Portal
What Works Research-Based Recommendation 2: Utilize assessment measures throughout high school so that students are aware of how prepared they are for college, and assist them in overcoming deficiencies as they are identified.
| Provide test preparation activities for 8th graders for ACT's Aspire or PSAT 8/9. Share results with families and advisors for course enrollment planning. | Tests/Test Preparation | [6 empty] | http://gearup.wa.gov/node/3770 | Portal
| Provide test preparation activities to help 8th and 10th grade students meet standard on SBA (Math & ELA) and MSP (Science) for 8th graders. | Tests/Test Preparation | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade8.aspx | Portal
| Provide test preparation activities for 9th graders on ACT's Aspire or PSAT. Share results with families and advisors for course enrollment planning. | Tests/Test Preparation | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade9.aspx, www.khanacademy.org | Portal
| Provide test preparation activities for 10th graders in ACT's Aspire or PSAT. Running Start: Help students prepare for community college assessment. Share results with families and advisors for course enrollment planning. | Tests/Test Preparation | [6 empty] | http://gearup.wa.gov/node/3770 | Portal
| Provide test preparation activities in 11th grade: ACT, PSAT/NMSQT, SAT, &/or ASVAB. Running Start: Help students prepare for community college assessment. Share results with families and advisors for course enrollment planning. | Tests/Test Preparation | [6 empty] | http://gearup.wa.gov/node/3770 | Portal
| Provide test preparation activities in 12th grade: Accuplacer or community college assessment. Share results with families and advisors for course enrollment planning. | Tests/Test Preparation | [6 empty] | https://accuplacer.collegeboard.org/student/practice | Portal
Administer the Accuplacer.
What Works Research-Based Recommendation 3: Surround students with adults and peers who build and support their postsecondary education aspirations.
| National GEAR UP Week: You are required to hold at least one event during this week. You are encouraged to conduct your student and family orientations during this time, or provide another “kick-off” event to celebrate GEAR UP. | Other | Sept. 23-29, 2018 | [5 empty] | http://gearup.wa.gov/about/impact/national-gear-week | Portal
| Provide GEAR UP Student Orientation to 7th-12th grade students. | Student Orientation | No later than October 31 | [5 empty] | WAGU Templates | Portal
| Provide career exploration activities so that 7th-12th grade students can learn about careers. | Counseling/Advising/Academic Planning/Career Counseling or Student Workshops | [6 empty] | http://careerbridge.wa.gov/ | Portal
| Provide college exploration activities so that 7th-12th grade student can learn about postsecondary schools or programs. | Counseling/Advising/Academic Planning/Career Counseling or Student Workshops | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade7.aspx | Portal
| Assist 9th-12th grade students in developing and revising their high school course plan to ensure they will meet the minimum college admissions standards. Encourage students to take dual credit and other challenging courses. | Counseling/Advising/Academic Planning/Career Counseling | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade9.aspx | Portal
| Provide career exploration activities so that (9-12 grade) students can learn about three or more careers. | Counseling/Advising/Academic Planning/Career Counseling or Student Workshops | [6 empty] | http://careerbridge.wa.gov/ | Portal
| Provide college exploration activities so that 9th-12th grade students can learn about five to ten postsecondary schools or programs that align with career interests. | Counseling/Advising/Academic Planning/Career Counseling or Student Workshops | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade9.aspx | Portal
| Assist in student-led conferences for 7th-12th grades. | Family Events-Counseling and Advising | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade7.aspx | Portal
| Assist in advisory program such as Career Guidance Washington. | Counseling/Advising/Academic Planning/Career Counseling | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade7.aspx | Portal
| Establish mentoring program such as Check and Connect or similar targeting 7th-12th grade students at risk of failing classes, falling behind academically, or with attendance issues. | Comprehensive Mentoring | [6 empty] | Check and Connect/Mentoring Works | Portal
| Meet w/ students who are off track on meeting grad requirements. | Counseling/Advising/Academic Planning/Career Counseling | [6 empty] | MTSS/Check & Connect | Portal
What Works Research-Based Recommendation 4: Engage and assist students in completing critical steps for college entry.
| Organize a visit to a vocational program AND a 2- and a 4-year schools by end of 9th grade. | College Visit | [6 empty] | http://gearup.wa.gov/node/3547 | Portal
| Offer job-site or vocational school program visit to learn about career options in 10th and 11th grades. | Job Shadow | [7 empty] | Portal
| Offer one postsecondary program or campus that is aligned with career interest in 11th grade. | College Visit | [6 empty] | http://gearup.wa.gov/node/3547 | Portal
| Promote summer camp opportunities. Coordinate on-site camp activities for 7th-12th graders. | Summer Programs - Fee Only | June-July-August 2019 | [5 empty] | Will be provided with a menu of options. | Portal
| Host the 12th Year Campaign in 12th grade. |  | Oct.-Nov. | [5 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Assist 12th grade students in completing 3 or more postsecondary applications. | [7 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Assist 12th grade students and families in completing the WASFA and FAFSA. |  | Oct.-Nov. | [5 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Assist 12th grade students and Families with Student Aid Reports (SAR). |  | Feb. | [5 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Help 12th grade students and families w/ financial aid award comparison. |  | April | [5 empty] | http://readysetgrad.org/educators/grad/12th-year-campaign
| Host Decision Day or College Signing Day for 12th grade students. |  | May | [5 empty] | http://www.readysetgrad.org/signing-day
| Help graduating seniors sign up for Summer Camp/Bridge. | Summer Programs - Academic Enrichment, Summer Programs-Fee Only, or Summer Programs-Remedial | July-Aug.
| Participate in Texting Campaign for 12th grade students. |  | July-Aug.
| Host transition activities for 12th grade students. |  | Apr-Jun. | [5 empty] | http://www.gearup.wa.gov/node/3553
What Works Research-Based Recommendation 5: Increase families’ financial awareness, and help students apply for financial aid.
| Hold events/workshop to teach 7th-12th grade students about going to college and financial aid. | Financial Aid Counseling/Advising | [6 empty] | http://gearup.wa.gov/resources/washington-state-gear-resources | Portal
| Provide a financial literacy curriculum to 7th-12th grade students that meets the state standards. | Financial Aid Counseling/Advising | [6 empty] | https://www.hsfpp.org | Portal
| Help 9th-12th grade students update Washboard scholarship profile & CBS contact information. | Financial Aid Counseling/Advising | [7 empty] | Portal
| Sign up 7th and 8th grade students for College Bound Scholarship. | Financial Aid Counseling/Advising | [6 empty] | http://www.readysetgrad.org/college/college-bound-scholarship-program | Portal
| Hold College Bound Scholarship Re-Pledge activities for 9th grade students and families. Remind students of the Pledge. Use the Repledge activity to engage students around future planning and various education pathways. | Financial Aid Counseling/Advising | [6 empty] | https://www.wcan.org/college-bound/college-bound-scholarship-re-pledge | Portal
| Promote scholarships and provide assistance in 12th grade. |  | Sept. -Jun.
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Family Activities
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
What Works Research-Based Recommendation 5: Increase families’ financial awareness, and help students apply for financial aid.
| Provide a minimum of three (3) workshops per year in 7th-12th grades to help families understand how to prepare for careers and college, including high school graduation requirements, college entrance requirements, financial aid, scholarships, and financial literacy. | Family Events | [6 empty] | http://www.gearup.wa.gov/file/family-engagement-resource-guide | Portal
| Provide a Family Event: Family Orientation | Family Event - Orientation or Celebratory | No later than October 31 | [5 empty] | WAGU Templates | Portal
| Family Event #1 | Family Events | Fall | [5 empty] | http://gearup.wa.gov/resources/family-workshop-presentations | Portal
| Family Event #2 | Family Events | Winter | [5 empty] | http://gearup.wa.gov/resources/family-workshop-presentations | Portal
| Family Event #3 | Family Events | Spring | [5 empty] | http://gearup.wa.gov/resources/family-workshop-presentations | Portal
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities

## 8th Grade Only
Steps will be highlighted if A and R are not assigned.
[5 empty] | R: | Does the step
Grade-Level RACI Chart |  |  |  |  | A: | Accountable for the step
[5 empty] | C: | Consulted with before the step
[5 empty] | I: | Informed when the step is completed
| Category: | Project Administration
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| GEAR UP team (at least one district administrator, at least one building administrator, school counselor(s), all GEAR UP paid staff, and other school staff such as class advisors) shall meet at least monthly to ensure that the work plan is followed. | N/A | [6 empty] | Workplan | N/A
| Submit match documentation including a summary of all match collected and the backup documentation from each contributor or source. | N/A | The 25th of each month | [5 empty] | http://gearup.wa.gov/grant-management | In-Kind Match Form (Goods & Services) In-Kind Match Form (School & Staff) Monthly Match Summary Form
| Submit GEAR UP expenditures for reimbursement. | N/A | The 25th of each month | [5 empty] | http://gearup.wa.gov/grant-management | A19, Travel Expense Voucher
| Participate in annual site visits with WSAC-Washington State GEAR UP staff and/or the external evaluators to ensure program compliance and effectiveness. | N/A | As scheduled. | R |  |  | R
| Track student, family, and staff participation in GEAR UP sponsored activities using program sign-in sheets. Activity and participation data will be entered electronically at least weekly into the WSAC-Washington State GEAR UP portal/database. | N/A | Weekly | R |  |  |  |  | http://gearup.wa.gov/grant-management
| Submit an annual work plan and budget. | N/A | 2018-06-30 | [5 empty] | Templates and instructions will be provided.
| When requested, administer and collect student and parent surveys and meet minimum return rates. | N/A | Annually, spring | R |  |  |  |  | Surveys will be provided.
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Professional Development
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Attend GEAR UP West Conference. | GEAR UP Sponsored Professional Development | Ocotber 14-16, 2018, Boise | [5 empty] | http://gearup.wa.gov/about/what-we-do/gear-west | Portal
| Attend WAGU Winter Workshop | GEAR UP Sponsored Professional Development | March | [5 empty] | http://gearup.wa.gov/calendar | Portal
| Attend WAGU Spring Workshop | GEAR UP Sponsored Professional Development | April | [5 empty] | http://gearup.wa.gov/calendar | Portal
| Attend Summer WAGU Kick-Off and Training Workshop. | GEAR UP Sponsored Professional Development | August | [5 empty] | http://gearup.wa.gov/calendar | Portal
| Conduct a Staff Orientation and Match Training | GEAR UP Sponsored Professional Development | No later than October 31
| Watch WAGU webinars. | GEAR UP Sponsored Professional Development | Nov, Dec, Jan, Feb, Apr, May | [5 empty] | https://www.youtube.com/channel/UC8v9AT7pG9bWwf9XcBYQptA | Portal
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Staff Activities
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Make GEAR UP sponsored professional development available to all appropriate staff at both the middle and high school levels. | GEAR UP Sponsored Professional Development | [6 empty] | Workshops, GoAlliance Couses, NCAN Elearning | Portal
| Provide a program orientation and match training to all building staff to ensure that they understand the program and the opportunities available to them. The match training must include what is allowable as match and how to document match accurately using GEAR UP forms. | Pro-Dev Staff Orientation and Match Training | No later than October 31 | [5 empty] | Washington State GEAR UP training templates | Portal
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Advisory Committee
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
| Establish an advisory committee and convene twice per year to provide guidance and build community acceptance and support of GEAR UP, and create a college-going culture within the school and community. |  | 2 per year | [6 empty] | Agendas and meeting minutes from these meetings must be kept on file and available for site visits. Submit roster, meeting agendas and minutes to WSAC via the portal.
GEAR UP Advisory Committee Meeting #1
GEAR UP Advisory Committee Meeting #2
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Student Activities
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
What Works Clearinghouse Recommendation 1: Offer courses and curricula that prepare students for postsecondary level work and ensure that students understand what constitutes a postsecondary-ready curriculum by 9th grade.
| Assist students in successfully beginning their High School and Beyond Plan. | Counseling/Advising/Academic Planning/Career Counseling | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade8.aspx | Portal
| Provide tutoring and homework help to help students earn a minimum cumulative GPA of 3.0 on a 4.0 scale. | Tutoring and Homework Assistance | [7 empty] | Portal
| Assist students in successfully completing pre-algebra. | Tutoring and Homework Assistance | [7 empty] | Portal
| Host transition activities for 8th grade students. | Counseling/Advising/Academic Planning/Career Counseling | Apr-Jun. | [6 empty] | Portal
| Support academic/remedial summer experiences to ensure students stay on track to graduate. | Summer Programs - Academic Enrichment, Summer Programs-Fee Only, or Summer Programs-Remedial | [7 empty] | Portal
What Works Research-Based Recommendation 2: Utilize assessment measures throughout high school so that students are aware of how prepared they are for college, and assist them in overcoming deficiencies as they are identified.
| Provide test preparation activities for ACT's Aspire or PSAT 8/9. Share results with families and advisors for course enrollment planning. | Tests/Test Preparation | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade8.aspx | Portal
| Provide test preparation activities to help students meet standard on SBA (Math & ELA) and MSP (Science). | Tests/Test Preparation | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade8.aspx | Portal
What Works Research-Based Recommendation 3: Surround students with adults and peers who build and support their postsecondary education aspirations.
| National GEAR UP Week: You are required to hold at least one event during this week. You are encouraged to conduct your student and family orientations during this time, or provide another “kick-off” event to celebrate GEAR UP. | Other | September 23-28, 2018 | [5 empty] | http://gearup.wa.gov/about/impact/national-gear-week | Portal
| Provide GEAR UP Student Orientation. | Student Orientation | No later than October 31 | [5 empty] | WAGU Templates | Portal
| Provide career exploration activities so that students can learn about careers. | Counseling/Advising/Academic Planning/Career Counseling or Student Workshops | [6 empty] | http://careerbridge.wa.gov/ | Portal
| Provide college exploration activities so that student can learn about postsecondary schools or programs. | Counseling/Advising/Academic Planning/Career Counseling or Student Workshops | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade8.aspx | Portal
| Assist in advisory program such as Career Guidance Washington. | Counseling/Advising/Academic Planning/Career Counseling | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade7.aspx | Portal
| Assist in student-led conferences. | Family Events-Counseling and Advising | [6 empty] | http://www.k12.wa.us/SecondaryEducation/CareerCollegeReadiness/CareerGuidanceWA/Grade8.aspx | Portal
| Establish mentoring program such as Check and Connect or similar targeting students at risk of failing classes, falling behind academically, or with attendance issues. | Comprehensive Mentoring | [6 empty] | Check and Connect/Mentoring Works | Portal
| Meet w/ students who are off track on meeting grad requirements. | Counseling/Advising/Academic Planning/Career Counseling | [6 empty] | MTSS/Check & Connect | Portal
What Works Research-Based Recommendation 4: Engage and assist students in completing critical steps for college entry.
| Visit a vocational program, a 2- and a 4-year schools by end of 9th grade. | College Visit | [6 empty] | http://gearup.wa.gov/node/3547 | Portal
| Promote summer camp opportunities. Coordinate on-site camp activities. | Summer Programs - Fee Only | June-July-August 2019 | [5 empty] | https://gearup.wa.gov/file/summer-camp-menu | Portal
What Works Research-Based Recommendation 5: Increase families’ financial awareness, and help students apply for financial aid.
| Sign up students for College Bound Scholarship/Update contact information if needed. | Financial Aid Counseling/Advising | [6 empty] | http://www.readysetgrad.org/college/college-bound-scholarship-program | Portal
| Hold events/workshop to teach students about going to college and financial aid. | Financial Aid Counseling/Advising | [6 empty] | http://gearup.wa.gov/resources/washington-state-gear-resources | Portal
| Provide a financial literacy curriculum that meets the state standards. | Financial Aid Counseling/Advising | [6 empty] | https://www.hsfpp.org | Portal
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities
| Category: | Family Activities
| Activity | Service Definition | Date | GU Coordinator | Grad Specialist | Counselor | Principal | Teacher | Resources | Data Collection, Documentation, Evaluation and Reporting
What Works Research-Based Recommendation 5: Increase families’ financial awareness, and help students apply for financial aid.
| Provide a minimum of three (3) workshops per year to help families understand how to prepare for careers and college, including high school graduation requirements, college entrance requirements, financial aid, scholarships, and financial literacy. | Family Events | [6 empty] | WAGU Templates | Portal
| Provide a Family Event: Family Orientation | Family Event - Orientation or Celebratory | No later than October 31 | [5 empty] | https://gearup.wa.gov/resources/family-workshop-presentations | Portal
| Family Event #1:Planning for college: High school graduation & college admissions requirements, Creating a HSBP | Family Events | Fall | [5 empty] | https://gearup.wa.gov/resources/family-workshop-presentations | Portal
| Family Event #2: Understanding college costs, Financial aid & scholarships including College Bound Scholarship sign-up events | Family Events | Winter | [5 empty] | https://gearup.wa.gov/resources/family-workshop-presentations | Portal
| Family Event #3: 9th grade transition, how to work with school counselor | Family Events | Spring | [5 empty] | https://gearup.wa.gov/resources/family-workshop-presentations | Portal
| List tasks related to this activity. Add rows if needed. |  | Assign dates | Identify roles and responsibilities